## Sheet1
To make it easier to complete this activity a list of the missing tasks is provided on the right
side of the Work Breakdown Structure. |  |  |  | You can copy and paste the missing tasks to the WBS.
Tasks | TASKS |  |  |  | List of the missing tasks in the Work Breakdown Structure to guide you in this exercise
Problem Definition |  |  |  |  | Modify innerpage based on discussion
| Conceptualization |  |  |  | Discuss innerpage design
|  | Drafting Concept Paper |  |  | Deployment
|  |  | Discussion/Finalization of concept paper |  | Write HTML code for innerpages
View and discuss the innerpages
| Creating Acceptance Criteria |  |  |  | Finalize innerpage design
|  | Interviewing Stakeholders |  |  | Finalize innerpages
|  | Documentation of Acceptance Criteria |  |  | Test if every page, link, button, tab, etc.. is working
| Define Broad/General Scope Objectives |  |  |  | Uploading finished product to Webserver
|  | Discussion/Agreement on the Objectives |  |  | Migration
|  | Finalization/Documentation of Objectives |  |  | Writing concept paper
Planning and Design |  |  |  |  | Define project scope objectives
| Project Plan |  |  |  | Write website scope objectives
Discussion/Agreement about Project Role
|  |  | Discuss/Finalize project scope objectives |  | Documentation of materials needed
|  |  | Write project scope objectives |  | Create the site map for the website
|  | Define Website scope objectives |  |  | Budget Plan
|  |  | Discuss/finalize website scope objectives |  | Research information about subject
Discuss/agree on the relevance of the content
|  | Define scope of work |  |  | Finalize and document information
|  |  | Discuss/finalize scope of work |  | Finalize the site map for the website
|  |  | Write scope of work |  | Innerpage Design
| Inventory of IT Project Resources |  |  |  | Finalization and documentation of the budget
|  | Identification of Human Resources |  |  | Add design elements to inner page wireframe layout
Documentation of Member Role in the Project
Identification of Material Resources
Discussion/Agreement on Materials needed
Preparing a Budget Plan
Determine project budget
Discussion and agreement on the budget
Look for additional sources of funding
Content gathering
Interview contact/resource persons
Research information on library/ search online for info
Take necessary pictures/video
Organize and document research materials
Edit and proofread content
Site Map
Developing the site map
IT Project Schedule
Create Gantt Chart
Discuss/agree on the timetable
Finalize and document timetable
Development
Graphics Design
Homepage Design
Designing homepage based on wireframe
Discuss homepage design
Redesign homepage according to discussion
Finalize homepage design
Designing innerpage based on wireframe
Redesign innerpage according to discussion
Finalize website wireframe
Submit to teacher the website wireframe
Approval of website wireframe
HTML Content-Integration
Homepage Content-Integration
Write HTML code for homepage
Integrate content materials to HTML code
View and discuss the initial homepage
Modify homepage based on discussion
Finalize homepage
Innerpage Content-Integration
Integrate content materials to HTML code
Modify innerpage based on discussion
Testing
First testing process (white box testing)
Test compliance to acceptance criteria
Test functionality
Resolve issues associated with functionality
Test content organization
Check grammar, spelling and bibliography
Edit corrections in the content
Test appearance and design aspects of website
Check its proximity with wire frame
Check appearance on different browsers
Check quality of pictures
Check overall appearance of website project
Resolve design issues with website
Final approval of the website project
Submit website project to the teacher
Modify or enhance website based on the suggestions of the teacher
Submit website project with modifications
Maintenance
Technical Support
Troubleshoot issues encountered by users in the website
Inform users that the issues have been resolved
Document solutions to the issues that were encountered
Updating website content
Update pictures
Take photographs
Upload photographs
Update text
Write updated text
Upload updated text
Modify design elements
Change icons
Change background
Change layout
Change color scheme