## Project Schedule
Task Number | Tasks | Duration in Days | Start Date | Target Deadline | Status | New Start Date | New Deadline | Predecessors | Resources
1 | Problem Definition | 5 | 2006-09-04 | 2006-09-08
1.1 | Conceptualization | 1 | 2006-09-04 | 2006-09-05
1.1.1 | drafting concept paper | 1 | 2006-09-04 | 2006-09-04
1.1.1.1 | discussion/finalization of concept paper | 1 | 2006-09-04 | 2006-09-04 |  |  |  | 1 | project team
1.1.1.2 | writing concept paper | 1 | 2006-09-05 | 2006-09-05 |  |  |  | 2 | content writer
1.2 | Creating Acceptance Criteria | 1 | 2006-09-06 | 2006-09-07
1.2.1 | interviewing stakeholders | 1 | 2006-09-06 | 2006-09-06 |  |  |  | 3 | project team
1.2.2 | documentation of acceptance critieria | 1 | 2006-09-07 | 2006-09-07 |  |  |  | 4 | content writer
1.3 | Define Broad/General Scope Objectives | 1 | 2006-09-08 | 2006-09-08
1.3.1 | discussion/agreement on objectives | 1 | 2006-09-08 | 2006-09-08 |  |  |  | 5 | project team
1.3.2 | finalization/documentation of objectives | 1 | 2006-09-08 | 2006-09-08 |  |  |  | 6 | content writer/ project manager
2 | Planning and Design
3 | Development
4 | Testing
5 | Deployment
6 | Maintenance

## Gantt chart
Task Number | Tasks | 2013-09-04 | 2013-09-05 | 2013-09-06 | 2013-09-07 | 2013-09-08 | 2013-09-10 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-14 | 2013-09-15 | 2013-09-16 | 2013-09-17 | 2013-09-18 | 2013-09-19 | 2013-09-20 | 2013-09-21
1 | Problem Definition | bar: 2013-09-04 to 2013-09-08
1.1 | Conceptualization | bar: 2013-09-04 to 2013-09-05
1.1.1 | drafting concept paper | bar: 2013-09-04
1.1.1.1 | discussion/finalization of concept paper | bar: 2013-09-04
1.1.1.2 | writing concept paper | bar: 2013-09-05
1.2 | Creating Acceptance Criteria | bar: 2013-09-06 to 2013-09-07
1.2.1 | interviewing stakeholders | bar: 2013-09-06
1.2.2 | documentation of acceptance critieria | bar: 2013-09-07
1.3 | Define Broad/General Scope Objectives | bar: 2013-09-08
1.3.1 | discussion/agreement on objectives | bar: 2013-09-08
1.3.2 | finalization/documentation of objectives | bar: 2013-09-08
2 | Planning and Design
3 | Development
4 | Testing
5 | Deployment
6 | Maintenance
Instructions:
1. Place all the tasks and the subtasks in the Tasks column.
2. Put the corresponding task number in the Task Number
column.
3. Replace the dates in the example with the actual timeline of your project.
4. The intersection of the date and the tasks or subtasks that is colored indicates that you are working on your project on that
particular day.
5. You can right click on a cell that is equivalent to a working day and change the color of the cell according to your preference.
Indicates that the task started at 9/4/2013 and ended at 9/8/2013
Subtasks were all started and finished on the same day 9/8/2013
Use the same color for subtasks that are under one major subtask to make it easier to distiguish them
In this example, all subtasks under task number 1.1 Conceptualization, task number 1.2 Creating Acceptance Criteria and task number 1.3 Define General Scope Objectives have the same color codes.
1.To change the color of a cell right click on a cell.
2.Choose Format Cells.
3.Click on the Patterns tab.
4.Choose the color that you want to use.