## Project Schedule
Task Number | Tasks | Duration in Days | Start Date | Target Deadline | Status | New Start Date | New Deadline | Predecessors | Resources
7 | Graphics Design | 26 | 2006-09-01 | 2006-10-06 | Delayed
7.1 | Home page Design | 11 | 2006-09-01 | 2006-09-15 | delayed |  |  | 1
7.1.1 | Designing home page based on wireframe | 4 | 2006-09-01 | 2006-09-06 | delayed |  |  | 1
7.1.1.1 | Add design elements to home page wireframe layout | 3 | 2006-09-01 | 2006-09-05 | delayed | 2006-09-06 | 2006-09-11 | 1 | graphic artist
7.1.1.2 | Insert pictures for home page wireframe | 1 | 2006-09-06 | 2006-09-06 | Not Completed |  |  | 2 | graphic artist
7.1.2 | Discuss home page design | 2 | 2006-09-07 | 2006-09-08 | Not Completed |  |  | 3 | project team
7.1.3 | Redesign home page based on discussion | 3 | 2006-09-11 | 2006-09-13 | Not Completed |  |  | 4 | graphic artist
7.1.4 | Finalize home page design | 2 | 2006-09-14 | 2006-09-15 | Not Completed |  |  | 5 | graphic artist
7.2 | Inner page design | 11 | 2006-09-18 | 2006-10-02 | Not Completed |  |  | 6
7.2.1 | Designing inner page based on wireframe | 4 | 2006-09-18 | 2006-09-21 | Not Completed |  |  | 6
7.2.1.1 | Add design elements to inner page wireframe layout | 3 | 2006-09-18 | 2006-09-20 | Not Completed |  |  | 6 | graphic artist
7.2.1.2 | Insert pictures for inner page wireframe | 1 | 2006-09-21 | 2005-09-21 | Not Completed |  |  | 7 | graphic artist
7.2.2 | Discuss inner page design | 2 | 2006-09-22 | 2006-09-25 | Not Completed |  |  | 8 | project team
7.2.3 | Redesign inner page based on discussion | 3 | 2006-09-26 | 2006-09-28 | Not Completed |  |  | 9 | graphic artist
7.2.4 | Finalize inner page design | 2 | 2006-09-29 | 2006-10-02 | Not Completed |  |  | 10 | graphic artist
7.3 | Finalize website wireframe | 2 | 2006-10-03 | 2006-10-04 | Not Completed |  |  | 11
7.3.1 | Submit to teacher the website wireframe | 1 | 2006-10-05 | 2006-10-05 | Not Completed |  |  | 12 | project team
7.3.2 | Approval of website wireframe | 1 | 2006-10-06 | 10/62006 | Not Completed |  |  | 13

## Gantt chart
Task Number | Tasks | 2013-09-01 | 2013-09-02 | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-06 | 2013-09-07 | 2013-09-08 | 2013-09-09 | 2013-09-10 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-14 | 2013-09-15 | 2013-09-16 | 2013-09-17 | 2013-09-18 | 2013-09-19 | 2013-09-20 | 2013-09-21 | 2013-09-22 | 2013-09-23 | 2013-09-24 | 2013-09-25 | 2013-09-26 | 2013-09-27 | 2013-09-28 | 2013-09-29 | 2013-09-30 | 2013-10-01 | 2013-10-02 | 2013-10-03 | 2013-10-04 | 2013-10-05 | 2013-10-06 | 2013-10-07 | 2013-10-08 | 2013-10-09 | 2013-10-10 | 2013-10-11 | 2013-10-12 | 2013-10-12 | 2013-10-12 | 2013-10-12
7 | Graphics Design
7.1 | Homepage Design
7.1.1 | Designing home page based on wire frame
7.1.1.1 | Add design elements to home page wire frame layout
7.1.1.2 | Insert pictures for home page wire frame
7.1.2 | Discuss home page design
7.1.3 | Redesign home page based on discussion
7.1.4 | Finalize home page design
7.2 | Inner page design
7.2.1 | Designing inner page based on wire frame
7.2.1.1 | Add design elements to inner page wire frame layout
7.2.1.2 | Insert pictures for inner page wire frame
7.2.2 | Discuss inner page design
7.2.3 | Redesign inner page based on discussion
7.2.4 | Finalize inner page design
7.3 | Finalize website wire frame
7.3.1 | Submit to teacher the website wire frame
7.3.2 | Approval of website wire frame