ISSUES LIST:

| Related Task | Issue | Proposed Action | Deadline | Person Accountable |
| --- | --- | --- | --- | --- |
| Create home page wireframe with design elements based on previous layout | Both graphic artists were absent during the scheduled day for the activity which is supposed to start on 09/01/06 | Both graphic artists would be available on Wednesday 09/06/06 to create the home page wireframe. | 09/11/06 | Maricar Salvosa (Graphic Artist), Ariadne Sta. Clara (Graphic Artist) |
| Insert pictures for home page | Digital photographs needed for the home page of the website, which are essential to the wireframe, were accidentally deleted. It is necessary to retake pictures that were lost. | The earliest available time to retake pictures would be on 09/11/06. | 09/11/06 | Maricar Salvosa (Graphic Artist) |
| Insert pictures for home page | Digital camera of the school will not be available on 09/11/06 or the whole week for that matter. | Borrow digital camera from a classmate who committed to lend his/her camera on 09/13/06. | 09/13/06 | Daphne Marcelo (Project Manager) |
| Insert pictures for home page | Budget for the transportation cost of retaking pictures is not enough. | Project partner will contribute additional funds for the project on 09/15/2006. | 09/15/06 | Maricar Salvosa (Graphic Artist) |
| Insert pictures for home page | Retake pictures. | The only available time to retake pictures will be on 09/18/2006. | 09/18/06 | Maricar Salvosa (Graphic Artist) |
| Insert pictures for home page | It appears that one of the graphic artists has a backup of the pictures that were lost and there is no need to retake pictures. Pictures will be available on 09/06/06 | Recover the pictures, adjust schedule, and the budget. | 09/12/06 | Ariadne Sta. Clara (Graphic Artist), Daphne Marcelo (Project Manager) |